# DRD进度控制列表DRD Schedule Control List

绿

黄

红

（1）项目Project（2）工作包Work package（3）阶段Stage

| 序号 No | DRD名称 DRD Name | 专业 Project | DID名称 DID Name | 编制者 Editor | 开始 日期 Start Date | 计划交付 日期 Delivery Date | 25% |  | 50% | 60% | 75% | 90% | 100% | 当前状态 Current Status | 备注 Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 支持专业 Support Specially | 日期 Date | 日期 Date | 校对及日期 Checker And Date | 审核及日期 Review And Date | 批准及日期 Approve And Date | 交付日期 Delivery Date |  |  |
| （4） | （5） | （6） | （7） | （8） | （9） | （10） | （11） | （12） | （13） | （14） | （15） | （16） | （17） | （18） | （19） |

注：此表为DRD进度控制列表样例，使用时可根据项目需求增减各列信息

Note: the table is an example of DRD Schedule control list, the information in each column can be added or removed according to the project

填写要求：

# Fill in requirements:

| - 对于短周期（不超过1个月）的DRD，工程项目人员可通过IPDT会议对DRD进度进行控制。 # For the short period DRD (not more than 1 month), engineering program profession can control the DRD schedule by IPDT meeting. - 对于长周期（超过1个月）的DRD，各专业负责人应向工程项目人员提供进度百分比的计划完成日期。 # For the long period DRD (more than 1 month) , DRD preparer should provide engineering program profession with the completion date of the schedule percentage.. 25%：已明确DRD对应的DID要求，对所负责的DRD需要的其他专业支持已识别清晰，所有编制输入信息准确、全面、有效，具备编制条件。 The corresponding DID requirements are clear, support from other profession has been identified, input conditions are ready, all input information is not only complete but accurate and effective .All the preparations are ready. 50%：DRD已完成初稿。 DRD has completed the first draft. 60%：DRD已完成校对。 DRD has been checked. 75%：DRD已完成审核。 DRD has been audited. 90%：DRD已完成批准。 DRD has been approved. |  | 100%：完成交付。officially issued. - 工程项目人员负责将计划日期填入DRD进度控制列表。在DRD达到规定的进度百分比时，可由DRD编制者随时报给工程项目人员，或由工程项目人员定期咨询DRD编制者等方式获得。 Engineering program profession is responsible for filling the plan date into the DRD schedule control list（FM 020-02）. When DRD reaches a specified percentage, it can be reported to engineering program profession by any DRD preparer at any time, or by regular consultation with DRD preparer by engineering program profession. - 工程项目人员应识别并标记当前状态（以红、黄、绿颜色表示）： Engineering program profession should identify and mark the "current status" of DRD by red, yellow, and green, the state is respectively: 红 红色 ：未按进度百分比计划完成，且无恢复计划。 Red :not completed per schedule, and no recovery plan, delayed 黄 黄色 ：未按进度百分比计划完成，但有恢复计划。 Yellow :not completed per schedule, but there is recovery plan 绿 绿色 ：按照进度百分比计划完成。 Green :complete per schedule - 当DRD进度控制列表中的“当前状态”出现黄色或红色时，应进行风险评估，按需进行风险管理。 Risk assessment shall be conducted if the "current status" of FM 020-02 is yellow or red ,performing risk management as needed. |
| --- | --- | --- |

填写说明：

Fill in Instructions:

- ：填写“项目名称”，如“MA700”。

Fill in "project name", such as"MA700".

- ：填写“工作包名称”，如“后机身”。

Fill in "work package name", such as "rear fuselage".

- ：填写“阶段代号”，如“D2.10”。

Fill in "phase code", such as"D2.10".

- ：填写“序号”，如“1”。

Fill in "serial number", such as"1".

- ：填写“DRD名称”，如“先行器材采购单（AMO）”。

Fill in "DRD name", such as "Advance Material Order".

- ：填写“专业代号及具体专业”，如“ASIL，结构”。适用专业参见GLC120110附录B及5.1节。

Fill in "specialty code and specific specialty", such as "ASIL, structure". Applicable majors refer to GLC120110 appendix B and section 5.1.

- ：填写“DID名称”，如“先行器材采购单的编制与发放说明”。

Fill in "DID name", such as "preparation and issuance of Advance Material Order".

- ：填写编制者的姓名。

Fill in the name of the compiler.

- ：填写编制开始时间，格式要求为YYYYMMDD。

Fill in the start time of compile in the format YYYYMMDD.

- ：填写计划交付日期，格式要求为YYYYMMDD。

Fill in the schedule delivery date in the format YYYYMMDD.

- ：填写“支持专业代码和名称”，如“SUPC，采购”。

Fill in "support specialty code and name" ,such as "SUPC, order".

- ：填写25%完成日期，格式要求为YYYYMMDD。

Fill in the 25% completion date in the format YYYYMMDD.

- ：填写50%完成日期，格式要求为YYYYMMDD。

Fill in the 50% completion date in the format YYYYMMDD.

- ：填写60%完成人姓名及日期，其中日期格式要求为YYYYMMDD。

Fill in the name and date of 60% completion in the format YYYYMMDD.

- ：填写75%完成人姓名及日期，其中日期格式要求为YYYYMMDD。

Fill in the name and date of 75% completion in the format YYYYMMDD.

- ：填写90%完成人姓名及日期，其中日期格式要求为YYYYMMDD。

Fill in the name and date of 90% completion in the format YYYYMMDD.

- ：填写100%完成日期，日期格式要求为YYYYMMDD。

Fill in the 100% completion date in the format YYYYMMDD.

- ：填写当期状态图例，使用表格右上角图例。

Fill in the current status legend, using the legend in the upper right corner of the table.

- ：按需填写未尽事宜。（1）-（19）由工程项目设计员填写。

Fill in the unmentioned matters as required.（1）-（19） Filled by Engineering Project.